## Info
Project Name | Selenium Final Project
CreatedBy / ExecutedBy | Oussama Achour
Delivery Date | 2023-05-22
Test Design Date | 2023-05-06
Designed By | Team1
Browsers | Google Chrome

## RegisterPage
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC001 | Verify that a user can successfully register as a customer on the website. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the website's header. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the registration form on the right side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field ( The password should be at least twelve characters long. To make it stronger, use upper and lower case letters, numbers, and symbols like ! " ? $ % ^ & ). | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Select " I am a customer " as the registratiuon type. | The " I am a customer " registration type should be selected | Pass
|  | 7- Click on the " Register " button to submit the form. | Clicking the " Register " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 8- Verify that the customer is redirected to the My Account page. | The customer should be redirected to the My Account page. | Pass
TC002 | Verify that a user can successfully register as a vendor on the website. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour | Bug001 | User will enter his password again after I m a vendor type selected | Low | Low
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the registration form on the right side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field ( The password should be at least twelve characters long. To make it stronger, use upper and lower case letters, numbers, and symbols like ! " ? $ % ^ & ). | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Select " I am a vendor " as the registratiuon type. | The " I am a vendor " registration type should be selected and new fields showing up ( First Name , Last Name , Shop Name , Shop URL , Phone Number ) | Pass
|  | 7- Enter a valid First Name, Last Name, Shop Name, Shop URL, and Phone Number in their respective fields. | The First Name, Last Name, Shop Name, Shop URL, and Phone Number fields should accept valid entries. | Pass
|  | 8- Click on the " Register " button to submit the form. | Clicking the " Register " button should submit the form and redirect you to the store configuration steps | Pass
|  | 9- Click on " Not right now " button to skip store configuration steps | Clicking the " Not right now " button should redirect you to the vonder dashboard page | Pass

## AddNewProduct
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC003 | Verify that a vendor can add a product to sell | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the login form on the left side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 7- Verify that the customer is redirected to the My Account page. | The customer should be redirected to the My Account page. | Pass
|  | 8- Click on the " Products" link located at the top left side of the Dashboard. | The "Products" link should be visible at the left side of the Dashboard. | Pass
|  | 9- Click on the " Add new product" button located at the right side of the Dashboard. | The "Add new product" button should be visible at the right side of the Dashboard. | Pass
|  | 10- Fill up the "Product Title" field with a valid product title. | The product title should be entered into the "Product Title" field. | Pass
|  | 11- Fill up the "Product Price" field with a valid product price. | The product price should be entered into the "Product Price" field. | Pass
|  | 12- Upload a product picture by clicking on the "Upload Picture" button and selecting a valid product image. | The product image should be uploaded by clicking the "Upload Picture" button. | Pass
|  | 13- Select the appropriate category for the product from the "Category" dropdown list. | The appropriate product category should be selected from the "Category" dropdown list. | Pass
|  | 14- Fill up the "Product Description" field with a valid product description. | The product description should be entered into the "Product Description" field. | Pass
|  | 15- Click on the "Create Product" button to save the product information. | The "Create Product" button should be clicked to save the product information. | Pass
|  | 16- Verify that the product has been successfully created and is now visible on the website by clicking on the "View Product" button. | The product should be successfully created and visible on the website. | Pass

## LoginAndLogoutPage
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC004 | Verify that a customer can log in to their account using their email and password, and are redirected to the My Account page. And Verify that customer can logout | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the login form on the left side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 7- Verify that the customer is redirected to the My Account page. | The customer should be redirected to the My Account page. | Pass
|  | 8- Click on the "My Account" icon located next to the "My Cart" icon. | The "My Account" menu should appear. | Pass
|  | 9- Scroll down to the "Logout" option. | The "Logout" option should be visible after scrolling down. | Pass
|  | 10- Click on "Logout" to log out of the account. | The user should be logged out and redirected to the "My Account" page. | Pass
TC005 | Verify that a vendor can log in to their account using their email and password, and are redirected to the Dashboard page. And verify that a vendor can logout | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the login form on the left side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and vendor should be redirected to the Dashboard page. | Pass
|  | 7- Verify that the vendor is redirected to the Dashboard page. | The vendor should be redirected to the Dashboard page. | Pass
|  | 8- Click on the "My Account" icon located next to the "My Cart" icon. | The "My Account" menu should appear. | Pass
|  | 9- Scroll down to the "Logout" option. | The "Logout" option should be visible after scrolling down. | Pass
|  | 10- Click on "Logout" to log out of the account. | The user should be logged out and redirected to the "My Account" page. | Pass

## ComparePage
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC006 | Verify that the Compare Page feature functions correctly for Logged-in Users. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4-Enter a valid Email address in the " Email address " field. Under the login form on the left side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 7- Click on the "Compare" icon located on the right side of the header next to the "Wishlist" icon. | The Compare page should be open and displayed on the screen. | Pass
|  | 8- Verify that the Compare page is empty | The Compare page should be empty. | Pass
|  | 9- Click on the "Return to Shop" link located in the middle of the page to go back to the shop. | User should navigate to the shop page. | Pass
|  | 10- Choose a product from the shop. Click on the product to view its details. | There are at least two products available on the website that can be added to the Compare Page | Pass
|  | 11- Click on the "Compare" link located right of the product picture on the center of the page next to the "Add to wishlist" button to add it to the compare page. | The selected product should be added to the Compare page. | Pass
|  | 12- Click on the "Shop" button located at the top right of the website's header to go back to the shop page. | User should be navigated back to the shop page. | Pass
|  | 13- Choose another product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 14- Click on the "Compare" link located right of the product picture on the center of the page next to the "Add to wishlist" button to add it to the compare page. | The selected product should be added to the Compare page. | Pass
|  | 15- Click on the "Compare" icon located on the right side of the header next to the "Wishlist" icon to go to the Compare page. | The Compare page should be displayed | Pass
|  | 16- Verify that the two products are displayed on the Compare page. | The two selected products should be displayed on the Compare page. | Pass
|  | 17- Remove the products from the Compare page by clicking on the "X" icon located at the bottom of each product. | The products should be successfully removed from the Compare page. | Pass
|  | 18- Verify that the Compare page is empty | The Compare page should be empty. | Pass
TC007 | Verify that the Compare Page feature functions correctly for Guest Users | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Compare" icon located on the right side of the header next to the "Wishlist" icon. | The Compare page should be open and displayed on the screen. | Pass
|  | 4- Verify that the Compare page is empty | The Compare page should be empty. | Pass
|  | 5- Click on the "Return to Shop" link located in the middle of the page to go back to the shop. | User should navigate to the shop page. | Pass
|  | 6- Choose a product from the shop. Click on the product to view its details. | There are at least two products available on the website that can be added to the Compare Page | Pass
|  | 7- Click on the "Compare" link located right of the product picture on the center of the page next to the "Add to wishlist" button to add it to the compare page. | The selected product should be added to the Compare page. | Pass
|  | 8- Click on the "Shop" button located at the top right of the website's header to go back to the shop page. | User should be navigated back to the shop page. | Pass
|  | 9- Choose another product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 10- Click on the "Compare" link located right of the product picture on the center of the page next to the "Add to wishlist" button to add it to the compare page. | The selected product should be added to the Compare page. | Pass
|  | 11- Click on the "Compare" icon located on the right side of the header next to the "Wishlist" icon to go to the Compare page. | The Compare page should be displayed | Pass
|  | 12- Verify that the two products are displayed on the Compare page. | The two selected products should be displayed on the Compare page. | Pass
|  | 13- Remove the products from the Compare page by clicking on the "X" icon located at the bottom of each product. | The products should be successfully removed from the Compare page. | Pass
|  | 14- Verify that the Compare page is empty | The Compare page should be empty. | Pass

## WishlistPage
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC008 | Verify that the Wishlist Page feature functions correctly for Logged-in Users. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | Email address : oussama_nyc@hotmail.fr , Password : Qwerty&1234567 Install Google Chrome Version 112.0.5615.137 on the test machine. The Oussama Achour website is accessible. The user has valid login credentials to access the website. There are at least two products available on the website that can be added to the wishlist Page. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the login form on the left side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 7- Click on the "Wishlist" icon located on the right side of the header next to the "Compare" icon. | The wishlist page should be open and displayed on the screen. | Pass
|  | 8- Verify that the Wishlist page is empty | The wishlist page should be empty. | Pass
|  | 9- Click on the "Shop" button located at the top right of the website's header to go to the shop page. | User should navigate to the shop page. | Pass
|  | 10- Choose a product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 11- Click on the "Add to wishlist" link located right of the product picture on the center of the page next to the "Add to Compare" link to add it to the wishlist page. | The selected product should be added to the wishlist page. | Pass
|  | 12- Click on the "Shop" button located at the top right of the website's header to go back to the shop page. | User should be navigated back to the shop page. | Pass
|  | 13- Choose another product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 14- Click on the "Add to wishlist" link located right of the product picture on the center of the page next to the "Add to Compare" link to add it to the compare page. | The selected product should be added to the wishlist page. | Pass
|  | 15- Click on the "wishlist" icon located on the right side of the header next to the "Compare" icon to go to the wishlist page. | The wishlist page should be displayed | Pass
|  | 16- Verify that the two products are displayed on the wishlist page. | The two selected products should be displayed on the wishlist page. | Pass
|  | 17- Remove the products from the wishlist page by clicking on the "X" icon located at the Left side of each product. | The products should be successfully removed from the wishlist page. | Pass
|  | 18- Verify that the 1st Product successfully removed | 1st Product should be removed | Pass
|  | 19- Verify that the 2nd Product successfully removed | 2nd Product should be removed | Pass
|  | 20- Verify that the wishlist page is empty | The wishlist page should be empty. | Pass
TC009 | Verify that the Wishlist Page feature functions correctly for Guest Users | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | Install Google Chrome Version 112.0.5615.137 on the test machine. The Oussama Achour website is accessible. There are at least two products available on the website that can be added to the wishlist Page. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Wishlist" icon located on the right side of the header next to the "Compare" icon. | The wishlist page should be open and displayed on the screen. | Pass
|  | 4- Verify that the Wishlist page is empty | The wishlist page should be empty. | Pass
|  | 5- Click on the "Shop" button located at the top right of the website's header to go back to the shop page. | User should navigate to the shop page. | Pass
|  | 6- Choose a product from the shop. Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 7- Click on the "Add to wishlist" link located right of the product picture on the center of the page next to the "Add to Compare" link to add it to the compare page. | The selected product should be added to the wishlist page. | Pass
|  | 8- Click on the "Shop" button located at the top right of the website's header to go back to the shop page. | User should be navigated back to the shop page. | Pass
|  | 9- Choose another product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 10- Click on the "Add to wishlist" link located right of the product picture on the center of the page next to the "Add to Compare" link to add it to the compare page. | The selected product should be added to the wishlist page. | Pass
|  | 11- Click on the "wishlist" icon located on the right side of the header next to the "Compare" icon to go to the wishlist page. | The wishlist page should be displayed | Pass
|  | 12- Verify that the two products are displayed on the wishlist page. | The two selected products should be displayed on the wishlist page. | Pass
|  | 13- Remove the products from the wishlist page by clicking on the "X" icon located at the Left side of each product. | The products should be successfully removed from the wishlist page. | Pass
|  | 14- Verify that the 1st Product successfully removed | 1st Product sould be removed | Pass
|  | 15- Verify that the 2nd Product successfully removed | 2nd Product sould be removed | Pass
|  | 16- Verify that the wishlist page is empty | The wishlist page should be empty. | Pass
TC010 | Verify that the functionality of adding wishlist items to the cart for logged-in users works as expected. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter a valid Email address in the " Email address " field. Under the login form on the left side | The email field should accept a valid email address | Pass
|  | 5- Enter a valid Password in the " Password " field | The Password field should accept a password that meets the site's password requirement. | Pass
|  | 6- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 7- Click on the "Wishlist" icon located on the right side of the header next to the "Compare" icon. | The wishlist page should be open and displayed on the screen. | Pass
|  | 8- Verify that the Wishlist page is empty | The wishlist page should be empty. | Pass
|  | 9- Click on the "Shop" button located at the top right of the website's header to go back to the shop page. | User should navigate to the shop page. | Pass
|  | 10- Choose a product from the shop. Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 11-Click on the "Add to wishlist" link located right of the product picture on the center of the page next to the "Add to Compare" link to add it to the compare page. | The selected product should be added to the wishlist page. | Pass
|  | 15- Click on the "wishlist" icon located on the right side of the header next to the "Compare" icon to go to the wishlist page. | The wishlist page should be displayed | Pass
|  | 16- Verify that the product are displayed on the wishlist page. | The two selected products should be displayed on the wishlist page. | Pass
|  | 17- Click on the "Add to Cart" link on the right of the product to add the product to the cart page | The product should be added to the cart. | Pass
|  | 18- Go to the cart page and check if the product is listed. | The product should be listed in the cart with the correct name, price, and quantity. | Pass

## CheckoutPage
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC011 | This test will ensure that a logged-in user can successfully add a product to their cart and complete the checkout process. By verifying that the user is able to successfully complete each step of the checkout process. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Enter valid Email and Password in the fields on the left side of the login form. | The fields should accept a valid email address and Password | Pass
|  | 5- Click on the " Log in " button to submit the form. | Clicking the " Log in " button should submit the form and customer should be redirected to the My Account page. | Pass
|  | 6- Click on the "Shop" button located at the top right of the website's header to go to the shop page. | User should navigate to the shop page. | Pass
|  | 7- Choose a product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 8- Verify that the product is available and in stock. | The product should be available and in stock. | Pass
|  | 9- Choose the desired quantity of the product to be added to the cart and Click on the "Add to Cart" button to add the product to the cart. | The product should be added to the cart with the desired quantity. | Pass
|  | 10- Verify that the selected product added to your cart. | Product should be added to the cart. | Pass
|  | 11- Click on the "View Cart" button to proceed to the cart page. | The cart page should be displayed | Pass
|  | 12- Click on the "Proceed to Checkout" button to proceed to the checkout page. | The checkout page should be displayed. | Pass
|  | 13- Fill in valid information in the required fields (First name, Last name, Country/Region, Street address, Town/City, State, ZIP Code, Phone, Order notes (optional)). | All required fields (First name, Last name, Country/Region, Street address, Town/City, State, ZIP Code, Phone) are filled with valid information. | Pass
|  | 14- Choose the payment method: "Check payments" or "Cash on delivery". | The selected payment method is displayed and can be chosen. | Pass
|  | 15- Accept the terms and conditions by ticking the checkbox. | The terms and conditions are displayed and can be accepted. | Pass
|  | 16- Click on the "Place order" button. | The order should be placed . | Pass
|  | 17- Verify that the order confirmation page is displayed and that the order details are correct. | The order should be confirmed. | Pass
TC012 | This test will ensure that a guest user can successfully add a product to their cart and complete the checkout process without having to create an account. By verifying that the guest user is able to successfully complete each step of the checkout process. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Shop" button located at the top right of the website's header to go to the shop page. | User should navigate to the shop page. | Pass
|  | 4- Choose a product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 5- Verify that the product is available and in stock. | The product should be available and in stock. | Pass
|  | 6- Choose the desired quantity of the product to be added to the cart and Click on the "Add to Cart" button to add the product to the cart. | The selected product should be added to the cart . | Pass
|  | 7- Verify that the selected product added to your cart. | Product should be added to the cart. | Pass
|  | 8- Click on the "View Cart" button to proceed to the cart page. | The cart page should be displayed | Pass
|  | 9- Click on the "Proceed to Checkout" button to proceed to the checkout page. | The checkout page should be displayed. | Pass
|  | 10- Fill in valid information in the required fields (First name, Last name, Country/Region, Street address, Town/City, State, ZIP Code, Phone, Order notes (optional)). | All required fields (First name, Last name, Country/Region, Street address, Town/City, State, ZIP Code, Phone) are filled with valid information. | Pass
|  | 11- Choose the payment method: "Check payments" or "Cash on delivery". | The selected payment method is displayed and can be chosen. | Pass
|  | 12- Accept the terms and conditions by ticking the checkbox. | The terms and conditions are displayed and can be accepted. | Pass
|  | 13- Click on the "Place order" button. | The order should be placed . | Pass
|  | 14- Verify that the order confirmation page is displayed and that the order details are correct. | The order should be confirmed. | Pass

## TrackYourOrderPage
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC013 | Verify that the order tracking functionality of the website works as intended and provides a good user experience. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | Email address : karim@gmail.com , Password : Qwerty&1234567 Orders ID : #5517 , #5518 Install Google Chrome Version 112.0.5615.137 on the test machine. The Oussama Achour website is accessible. The user has valid Oders ID and Billing email. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Track Your Order" link located at the top right corner of the top header next to the Shop link . | The " Track Your Order " link should be visible and clickable | Pass
|  | 4- Verify that the Order ID and Billing email fields are mandatory by leaving them empty and clicking on the "Track" button. | The user should be prompted to fill the Order ID field before they can proceed to the next step. | Pass
|  | 5- Verify that appropriate error messages are displayed when the user enters invalid input in either the Order ID or Billing email field. | The system should display an appropriate error message when the user enters invalid input or when the Order ID and/or Billing email do not match any orders in the system. | Pass
|  | 6- Verify that the order status is displayed correctly when the user enters valid input in both the Order ID and Billing email fields. | The system should fetch the order status associated with the entered Order ID and Billing Email and should display it accurately to the user. | Pass
|  | 7- Verify that the user is able to track other orders by entering a new Order ID. | The system allows the user to enter a new Order ID and tracks the new order status. | Pass

## Coupon
TC ID | Test Case Summary | Test Case Steps | Expected Result | Status | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC014 | This test case verifies that the user can apply a valid coupon code to get a discount on their purchase. The test case covers scenarios such as verifying the availability of the product, adding the product to the cart, verifying the coupon code field, applying a valid coupon code, and verifying the discount. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | Coupon Code : team1 ( 20$ off ) , Coupon Code : oussama75off ( 75% ) Expired Coupon , Coupon Code :oussama50off ( 50% ) , Coupon Code : MacBookPro30Off applied only to this product : Apple MacBook Pro MF841HN/A 13-inch Laptop. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Shop" link located at the top right corner of the top header next to the My Account link . | The " My Account " button should be visible and clickable | Pass
|  | 4- Choose a product from the shop, Click on the product to view its details. | The product should be available and in stock. | Pass
|  | 5- Verify that the product is available and in stock. | The selected product should be added to the cart . | Pass
|  | 6- Choose the desired quantity of the product to be added to the cart and Click on the "Add to Cart" button to add the product to the cart. | Product should be added to the cart. | Pass
|  | 7- Verify that the selected product added to your cart. | The cart page should be displayed | Pass
|  | 8- Click on the "View Cart" button to proceed to the cart page. | The checkout page should be displayed. | Pass
|  | 9- Verify that the coupon code field only accepts valid codes by entering an invalid code and verifying the error message. | The system displays an appropriate error message when an invalid code is entered in the coupon code field. | Pass
|  | 10- Verify that expired coupons cannot be used | The system displays an appropriate error message when the user tries to apply an expired coupon code. | Pass
|  | 11- Enter a valid coupon code in the coupon code field and click on the "Apply Coupon" button. | The system applies the coupon code and displays the discount amount on the cart page. | Pass
|  | 12- Verify that expired coupons cannot be used | The system displays an appropriate error message when the user tries to apply an expired coupon code. | Pass
|  | 13- Verify that specific coupons can only apply to specific products | Coupon code applied successfully to the specific products. | Pass

## ProductReviewsAndRatings
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC015 | Verify that the user is able to write a review and rate a product | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Shop" button located at the top right of the website's header to go to the shop page. | User should navigate to the shop page. | Pass
|  | 4- Choose a product from the shop, Click on the product to view its details. | The selected product's details should be displayed. | Pass
|  | 5- Select a star rating for the product from ( 1 to 5 ). | The selected star rating is highlighted. | Pass
|  | 6- Fill up the "Description" field with a valid review description. | The review description is filled with the entered text. | Pass
|  | 7- Fill up the "name" and the "email" fields with a valid name and email. | The name and email fields is filled with the entered text. | Pass
|  | 8- Verify that the success message "Your comment is awaiting approval" is displayed. | The success message "Review submitted successfully" is displayed. | Pass

## PasswordStrengthValidation
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC016 | Verify that the password field displays the appropriate message if the password does not meet the minimum security requirements. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | Enter a valid Email address in the " Email address " field. Under the registration form on the right side | The email field should accept a valid email address | Pass
|  | 4- Enter a Very weak strength password in the password field. | A message should be displayed under the password field indicating that the password is Very weak | Pass
|  | 5- Enter a weak strength password in the password field. | A message should be displayed under the password field indicating that the password is weak | Pass
|  | 6- Enter a Medium strength password in the password field. | A message should be displayed under the password field indicating that the password is Medium | Pass
|  | 7- Enter a Strong strength password in the password field. | A message should be displayed under the password field indicating that the password is Strong | Pass

## Filter
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC017 | Test the functionality of the filter feature | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Shop" button located at the top right corner of the website's header. | The "Shop" page should open. | Pass
|  | 4- Locate the filter option on the page | The filter option should be visible on the page. | Pass
|  | 5- Select the price range filter option | The selected filter option should be applied to the products displayed | Pass
|  | 6- Verify that the products displayed on the page have been filtered according to the selected filter option | Only the products that meet the selected filter option should be displayed on the page. | Pass
|  | 7- Clear the selected filter option | The selected filter option should be cleared. | Pass
|  | 8- Verify that the products displayed on the page have been reset to the default view | The products displayed on the page should be reset to the default view. | Pass

## Search
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC018 | Verify that the search feature on the website works as expected and returns accurate results | 1- Open Chrome browser. | Chrome browser should be displayed | Pass |  | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Enter a valid search query in the search box. | The search query is entered correctly and without any errors. | Pass
|  | 4- Click on the search button or press Enter. | The search feature returns relevant results without any errors. | Pass
|  | 5- Verify that the search results page is displayed and contains relevant results. | The search results page is displayed and contains relevant results. | Pass
|  | 6- Repeat the search with another query and verify the results. | The search new query is entered correctly and without any errors. | Pass
|  | 7- Verify that the search results page is displayed and contains relevant results. | The search results page displays relevant results for the new query entered. | Pass

## ContactUs
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC019 | Verify that the Contact Us page on the website is functioning correctly and that users are able to submit their inquiries without any issues. | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | The website is accessible and the Contact Us Page is available. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Navigate to the Contact Us page on the website. the Contact Us page link located on the middle of the footer of the home page. | The Contact Us page should load without any errors. | Pass
|  | 4- Fill in the required fields in the contact form, including Name, Email, and Comment or Message. | The user should be able to fill in the required fields in the contact form. | Pass
|  | 5- Click on the "Send Message" button. | Clicking on the "Submit" button should submit the form without any issues. | Pass
|  | 6 - Verify that the form has been submitted successfully by checking for the success message on the page. | The success message should be displayed on the page after successful form submission. | Pass

## ContactStoreVendor
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC020 | Verify that a user can send a message to a vendor store | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | The website is accessible and the Stores Page is available. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Stores" link located at the top right of the website's header to go to the Stores page. | he Stores page should open, displaying all the stores available on the website. | Pass
|  | 4- Enter the vendor store name in the search field and click the "Apply" button. | The search results page should display all the stores that match the vendor store name entered in the search field. | Pass
|  | 5- Click on the store name in the search results to access the store page. | The user should be able to access the store page by clicking on the store name. | Pass
|  | 6- Fill out the message form with a valid name, email, and message content. Click on the "Send Message" button to submit the message. | The user should be able to fill out the message form with a valid name, email, and message content. | Pass
|  | 7- Verify that a success message is displayed, confirming that the message was sent successfully. | A success message should be displayed, confirming that the message was sent successfully. | Pass

## DarkModeLightMode
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC021 | Verify that a user can change the site mode | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | The website has a feature to toggle between dark and light modes. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "Dark Mode" option | The site's mode should change to dark mode. | Pass
|  | 4- Check the color scheme and overall appearance to confirm it reflects a dark theme. | The site should have a dark theme, with appropriate colors and contrast. | Pass
|  | 5- Click on the "Light Mode" option. | The site's mode should change to light mode. | Pass
|  | 6- Check the color scheme and overall appearance to confirm it reflects a light theme. | The site should have a light theme, with appropriate colors and contrast. | Pass

## PasswordChange
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC022 | Verify that a user can change their password | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | The website has a feature to change the user's password. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the website's header. | The user should be redirected to their account details page. | Pass
|  | 4- Log in with valid credentials. | The user should be able to log in successfully with their valid credentials. | Pass
|  | 5- Click on the "Account details" link. | he user should be taken to the account details page where they can edit their information. | Pass
|  | 6- Enter the current password in the "Current Password" field. | The current password should be entered correctly in the "Current Password" field. | Pass
|  | 7- Enter a new password in the "New Password" field. | The new password should be entered correctly in the "New Password" field. | Pass
|  | 8- Confirm the new password in the "Confirm New Password" field. | The confirmation of the new password should match the entered new password in the "Confirm New Password" field. | Pass
|  | 9- Click on the "Save Changes" button. | After clicking the "Save Changes" button, the system should process the password change request. | Pass
|  | 10- Verify that the password change was successful. | The system should display a confirmation message or provide some indication that the password change was successful. The user should be able to log in with the new password. | Pass

## BillingShippingAddresses
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC023 | Verify that a user can change their Billing Adress | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | The website has a feature to change the user's billing address. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Log in with valid credentials. | The user should be able to log in successfully with their valid credentials. | Pass
|  | 5- Click on the "Addresses" link. | The user should be taken to the addresses section where they can manage their address information. | Pass
|  | 6- Click on the "Billing Address Edit" link. | The user should be able to access the billing address edit form. | Pass
|  | 7- Enter valid billing information in the appropriate fields. | The user should be able to enter valid billing information, such as street address, city, state, postal code, etc. | Pass
|  | 8- Click on the "Save Billing Address" button. | After clicking the "Save Billing Address" button, the system should process the request and save the new billing address. | Pass
|  | 9- Verify that the billing address changed successfully. | The system should display a confirmation message or provide some indication that the billing address change was successful. | Pass
TC024 | Verify that a user can change their Shipping Adress | 1- Open Chrome browser. | Chrome browser should be displayed | Pass | The website has a feature to change the user's shipping address. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" button located at the top right corner of the homepage. | The " My Account " button should be visible and clickable | Pass
|  | 4- Log in with valid credentials. | The user should be able to log in successfully with their valid credentials. | Pass
|  | 5- Click on the "Addresses" link. | The user should be taken to the addresses section where they can manage their address information. | Pass
|  | 6- Click on the "shipping Address Edit" link. | The user should be able to access the shipping address edit form. | Pass
|  | 7- Enter valid shipping information in the appropriate fields. | The user should be able to enter valid shipping information, such as street address, city, state, postal code, etc. | Pass
|  | 8- Click on the "Save shipping Address" button. | After clicking the "Save shipping Address" button, the system should process the request and save the new billing address. | Pass
|  | 9- Verify that the shipping address changed successfully. | The system should display a confirmation message or provide some indication that the shipping address change was successful. | Pass

## SignUpToNewsletter
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC025 | Verify that a user can Sign Up To Newsletter | 1- Open Chrome browse. | Chrome browser should be displayed | Pass | The website has a feature to sign up for a newsletter. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Sign up for the newsletter with an invalid email. | The user should be able to enter an email address that is not valid. | Pass
|  | 4- Verify that the error message is displayed successfully. | The system should display an error message indicating that the email is invalid or not in the correct format. | Pass
|  | 5- Sign up for the newsletter with a valid email. | The user should be able to enter a valid email address. | Pass
|  | 6- Verify that the confirmation message is displayed successfully. | The system should display a confirmation message indicating that the user has successfully signed up for the newsletter. | Pass

## UpdateCart
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC026 | Verify that a user can update their shopping cart | 1- Open Chrome browse. | Chrome browser should be displayed | Pass | The website is accessible and the shop Page is available. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3-Click on the "Shop" link. | The user should be taken to the shop page where products are listed. | Pass
|  | 4-Choose a product from the shop and click on the product to view its details. | The user should be able to click on a product to view its details. | Pass
|  | 5-Verify that the product is available and in stock. | The system should display the product details, including availability and stock information. | Pass
|  | 6-Choose the desired quantity of the product to be added to the cart. | The user should be able to select a desired quantity of the product. | Pass
|  | 7-Click on the "Add to Cart" button to add the product to the cart. | After clicking the "Add to Cart" button, the system should add the selected product to the user's cart. | Pass
|  | 8-Verify that the selected product is added to your cart. | The system should display a confirmation message or provide some indication that the product was successfully added to the cart. | Pass
|  | 9-Click on the "View Cart" button to proceed to the cart page. | The user should be able to navigate to the cart page to view the added products. | Pass
|  | 10- Type the updated quantity of the product in the product quantity field. | The user should be able to type the updated quantity of the product in the respective quantity field. | Pass
|  | 11- Click on the "Update Cart" button. | After clicking the "Update Cart" button, the system should update the cart with the new quantity. | Pass
|  | 12- Verify that the cart is successfully updated. | The system should display a confirmation message or provide some indication that the cart was successfully updated. | Pass

## ProductGallery
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC027 | Verify Product Gallery Functionality | 1- Open Chrome browse. | Chrome browser should be displayed | Pass | The website has a search functionality and The products has pictures | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Enter a valid search query in the search box. | The user should be able to enter a valid search query in the search box. | Pass
|  | 4- Click on the search button or press Enter. | After clicking the search button or pressing Enter, the system should display the search results page based on the entered query. | Pass
|  | 5- Click on the product gallery. | The user should be able to click on the product gallery, which may be in the form of thumbnails, arrows, or any other navigation element. | Pass
|  | 6- Click on the next product picture. | After clicking on the next product picture, the system should display the following picture in the gallery. | Pass
|  | 7- Verify that the next product picture is displayed. | The user should be able to verify that the next product picture is displayed correctly. | Pass

## PaymentMethodForVendor
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC028 | Add Payment Method" functionality | 1- Open Chrome browse. | Chrome browser should be displayed | Pass | The has a "My Account" section with registration and vendor functionality. The "Add Payment Method" functionality is available and functioning correctly. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" link. | The user should be able to click on the "My Account" link. | Pass
|  | 4- Register as a vendor. | The user should be able to register as a vendor. | Pass
|  | 5- Verify that the vendor is redirected to the Dashboard page. | After registering as a vendor, the system should redirect the user to the Dashboard page. | Pass
|  | 6- Click on the "Payment Methods" link. | The user should be able to access the "Payment Methods" section. | Pass
|  | 7- Click on "Add Payment Method." | The user should be able to click on the "Add Payment Method" option. | Pass
|  | 8- Enter a valid PayPal email address. | The user should be able to enter a valid PayPal email address. | Pass
|  | 9- Click on the "Update Settings" button. | After clicking the "Update Settings" button, the system should save the payment method information. | Pass
|  | 10- Verify that the payment method information has been saved. | The user should be able to verify that the payment method information has been successfully saved. | Pass

## PasswordRecovery
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC029 | Testing the "Lost Password" functionality | 1- Open Chrome browse. | Chrome browser should be displayed | Pass | The website has a "My Account" section with a "Lost Password" functionality. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the "My Account" link. | The user should be able to click on the "My Account" link. | Pass
|  | 4- Click on the "Lost your password?" link. | The user should be able to click on the "Lost your password?" link. | Pass
|  | 5- Enter an invalid email address. | The user should be able to enter an invalid email address. | Pass
|  | 6- Click on the "Reset Password" button. | After clicking the "Reset Password" button, the system should display an alert indicating that the username or email is invalid. | Pass
|  | 7- Verify that the "Invalid username or email" alert is displayed. | The user should be able to verify that the "Invalid username or email" alert is displayed. | Pass
|  | 8- Enter a valid email address. | The user should be able to enter a valid email address. | Pass
|  | 9- Click on the "Reset Password" button. | After clicking the "Reset Password" button, the system should display an alert indicating that the password reset email has been sent. | Pass
|  | 10- Verify that the "Password reset email has been sent" alert is displayed. | The user should be able to verify that the "Password reset email has been sent" alert is displayed. | Pass

## HomePageSlider
TC ID | Test Case Summary | Test Case Steps | Expected Result | Actual Result | Dependencies | Tester ( CreatedBy / ExecutedBy ) | Bug/Improvement Number | Note | Bug Severity | Priority
TC030 | Verify that the slider on the home page can be navigated correctly | 1- Open Chrome browse. | Chrome browser should be displayed | Pass | The website has a home page with sliders displaying products. | Oussama Achour
|  | 2- Navigate to oussama-achour.com. | The oussama-achour.com Website should load in google chrome | Pass
|  | 3- Click on the second slider. | The second slider should be selected and displayed. | Pass
|  | 4- Click on the button within the second slider. | After clicking the button within the second slider, the system should navigate to the associated product or perform the intended action. | Pass
|  | 5- Verify the product title text for the second slider product. | The product title text for the second slider product should be visible and accurate. | Pass
|  | 6- Click on the home page logo to return to the home page. | After clicking the home page logo, the system should return the user to the home page. | Pass
|  | 7- Click on the third slider. | The third slider should be selected and displayed. | Pass
|  | 8- Click on the button within the third slider. | After clicking the button within the third slider, the system should navigate to the associated product or perform the intended action. | Pass
|  | 9- Verify the product title text for the third slider product. | The product title text for the third slider product should be visible and accurate. | Pass
|  | 10- Click on the home page logo to return to the home page. | After clicking the home page logo, the system should return the user to the home page. | Pass